## 工作表1
Software Engineering Meeting Minutes
Date |  | 20210309
Time |  | 11:20~11:50
Location |  | CSIE Building Room 521
Facilitator |  | 鄒咏霖
Recorded by |  | 陳熙
Objective |  | Assign homework and plan for term project.
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member |  |  | v
陳熙 |  | r07922151@csie.ntu.edu.tw | Member |  |  | v
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member |  |  | v
Meeting Agendas
1. Survey Amazon - surveys its business models, products and services, and revenues, profits and etc. 2. Standish Group Chaos Repoert 2016~recent data 3. Survey DevOps 4. WBS 5. visit company接洽(先寄信確認意願，下次開會討論要問的問題) * kronos * microsoft 6. 閱讀課本的附錄Ａ：軟體工程個案研究–需求管理，並於三週後(3/23)報告
Issues
- 1.2.3.禮拜天結束前弄完ppt 1. Survey Amazon [name=鄒咏霖][name=陳熙] - surveys its business models, products and services, and revenues, profits and etc. 2. Standish Group Chaos Repoert 2016~recent data(弄成表格) [name=李辰暘] 3. Survey DevOps[name=鄒咏霖][name=李紹銘][name=侯思岑] 4. WBS [name=汪宸宇] (先列出需求分析) 5. visit company接洽(先寄信確認意願，下次開會討論要問的問題) * kronos [name=汪宸宇] * microsoft[name=李紹銘] 6. 閱讀課本的附錄Ａ：軟體工程個案研究–需求管理，並於三週後(3/23)報告[name=李紹銘]
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Reading paper |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Process sharing |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Web Framework Survey |  |  | All | 2021-03-08 | Closed
4 | Survey Amazon |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Ongoing
5 | Collect Standish Group Chaos Repoert 2016~recent data |  |  | 李辰暘 | 2021-03-14 | Ongoing
6 | Survey DevOps |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-14 | Ongoing
7 | WBS(Initial Requirement) |  |  | 汪宸宇 | 2021-03-22 | Ongoing
8 | Contact visiting company |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Ongoing
9 | Reading textbook |  |  | 李紹銘 | 2021-03-22 | Ongoing