## 工作表1
Software Engineering Meeting Minutes
Date |  | 20210313
Time |  | 21:00~21:42
Location |  | Skype
Facilitator |  | 鄒咏霖
Recorded by |  | 鄒咏霖
Objective |  | Disscussion about DevOps
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member
陳熙 |  | r07922151@csie.ntu.edu.tw | Member
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member
Meeting Agendas
1. 討論自己對於DevOps的看法 2. 分工誰要對哪個DevOps中的細項做更深入的調查與負責該部分的ppt
Issues
- DevOps - 每一步都要自動化 - 跨越連流程，是一種開發的文化、習慣。 - 可以在ppt中跟傳統比較 - Congifuration management[name=咏霖] - Issue tracking[name=紹銘] - 很亂，很多不同的定義 - 強調自動化，再出現bug時可以自動發issue通知相關developer - build process[name=紹銘] - Testing Environment[name=思岑] - Operational Environment[name=思岑] - Test - Integration:整個project - Unit:一個module - 如何減少develop和operation之隔閡 - 小改動就deploy，不要讓一次的更動太大，這樣可以減少資訊不對稱 - 自動化cover掉一些溝通 - code quality意義? - Resolve dependency? - waterfall develop - hard to change from feedback by customer - 一次性開發、Test、deploy - 多次小問題比一次大問題成本低，效率快
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Reading paper |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Process sharing |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Web Framework Survey |  |  | All | 2021-03-08 | Closed
4 | Survey Amazon |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Ongoing
5 | Collect Standish Group Chaos Repoert 2016~recent data |  |  | 李辰暘 | 2021-03-14 | Ongoing
6 | Survey DevOps |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-14 | Ongoing
7 | WBS(Initial Requirement) |  |  | 汪宸宇 | 2021-03-22 | Ongoing
8 | Contact visiting company |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Ongoing
9 | Reading textbook |  |  | 李紹銘 | 2021-03-22 | Ongoing