## 工作表1
Software Engineering Meeting Minutes
Date |  | 20210315
Time |  | 20:00~21:05
Location |  | CSIE Building Room 544
Facilitator |  | 鄒咏霖
Recorded by |  | 陳熙
Objective |  | Discuss about homework.
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member |  |  | v
陳熙 |  | r07922151@csie.ntu.edu.tw | Member |  |  | v
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member |  |  | v
Meeting Agendas
1. 確認03/09各項之進度 - Survey Amazon - Survey DevOps - WBS - visit company接洽 - 閱讀課本的附錄Ａ：軟體工程個案研究–需求管理
Issues
1. 確認03/09各項之進度 - Survey Amazon - [ppt](https://docs.google.com/presentation/d/1gHEF3zZANtV9RtQwMdv0KJGubVdzbyPVkcyKOeR-jMk/edit?usp=sharing) - Survey DevOps - 下周 - WBS - [需求分析](https://hackmd.io/0TYVRuuGRwCBijEXHfJ_1Q?view) - 科普 - visit company接洽 - 已經寄信(明天問老師microsoft) - 閱讀課本的附錄Ａ：軟體工程個案研究–需求管理[name=紹銘][name=思岑]
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Reading paper |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Process sharing |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Web Framework Survey |  |  | All | 2021-03-08 | Closed
4 | Survey Amazon |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Closed
5 | Collect Standish Group Chaos Repoert 2016~recent data |  |  | 李辰暘 | 2021-03-14 | Suspended
6 | Survey DevOps |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-22 | Ongoing
7 | WBS(Initial Requirement) |  |  | 汪宸宇 | 2021-03-22 | Ongoing
8 | Contact visiting company |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Ongoing
9 | Reading textbook |  |  | 李紹銘、侯思岑 | 2021-03-22 | Ongoing