## 工作表1
Software Engineering Meeting Minutes
Date |  | 2021-03-16
Time |  | 11:20~12:20
Location |  | CSIE Building Room 521
Facilitator |  | 鄒咏霖
Recorded by |  | 李辰暘
Objective |  | Discuss homework, company visits, and term project.
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member |  |  | v
陳熙 |  | r07922151@csie.ntu.edu.tw | Member |  |  | v
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member |  |  | v
Meeting Agendas
• WBS • Term project • Company visits • DevOps • Amazon • Textbook appendix A
Issues
• WBS • How to expand more items and estimate effort • Term project • Need to decide the features of the plaform (TradingView as an example) • Company visits • What if Microsoft does not reply • Come up with interview questions • DevOps • Presentation on 3/23 • Need to decide DevOps workflow for our project (e.g. Jenkins) • Amazon • Presentation on 3/23 • Focus on changes due to Covid-19 and how an IT company makes money • Textbook appendix A • Presentation on 3/23
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Prepare homework paper presentation. |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Come up with a real-life process. |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Survey web frameworks for term project. |  |  | All | 2021-03-08 | Closed
4 | Prepare Amazon presentation. |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Closed
5 | Collect Chaos Report 2016~2020 data. |  |  | 李辰暘 | 2021-03-14 | Closed
6 | Prepare DevOps presentation. |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-22 | Ongoing
7 | Propose initial requirements for WBS. |  |  | 汪宸宇 | 2021-03-22 | Ongoing
8 | Contact visiting company candidates. |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Ongoing
9 | Prepare textbook presentation. |  |  | 李紹銘、侯思岑 | 2021-03-22 | Ongoing
10 | Try Jenkins and decide whether to use it as our DevOps tool. |  |  | All | 2021-03-22 | Ongoing
11 | Build Jenkins server on CSIE workstation. |  |  | 陳熙 | 2021-03-22 | Ongoing
12 | Prepare interview questions for company visits (3 questions each member). |  |  | All | 2021-03-22 | Ongoing
13 | Decide primary features of our term-project platform. |  |  | All | 2021-03-22 | Ongoing