## 工作表1
Software Engineering Meeting Minutes
Date |  | 2021-05-03
Time |  | 20:00 ~ 22:30
Location |  | Online @Skype
Facilitator |  | 鄒咏霖
Recorded by |  | 侯思岑
Objective |  | Company visit presentation rehearsal and term-project class diagram discussion
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member |  |  | v
陳熙 |  | r07922151@csie.ntu.edu.tw | Member |  |  | v
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member |  |  | v
Meeting Agendas
1. Synology Presentation discussion and modification 2. Term-Project Class Diagram * ParameterSetter * File Storage&Underlying Asset Data * File Management Module
Issues
1. Kronos Presentation * Presented by 宸宇 2. Synology Presentation * Presented by 陳熙 3. Term-Project Class Diagram * Discuss the class diagrams of individual modules * Relation between class ParameterSet and Parameter
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Prepare homework paper presentation. |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Come up with a real-life process. |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Survey web frameworks for term project. |  |  | All | 2021-03-08 | Closed
4 | Prepare Amazon presentation. |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Closed
5 | Collect Chaos Report 2016~2020 data. |  |  | 李辰暘 | 2021-03-14 | Closed
6 | Prepare DevOps presentation. |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-22 | Closed
7 | Propose initial requirements for WBS. |  |  | 汪宸宇 | 2021-03-22 | Closed
8 | Contact visiting company candidates. |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Closed
9 | Prepare textbook presentation. |  |  | 李紹銘、侯思岑 | 2021-03-22 | Closed
10 | Try Jenkins and decide whether to use it as our DevOps tool. |  |  | All | 2021-03-22 | Closed
11 | Build Jenkins server on CSIE workstation. |  |  | 陳熙 | 2021-03-22 | Closed
12 | Prepare interview questions for company visits (3 questions each member). |  |  | All | 2021-03-22 | Closed
13 | Watch interviewing videos about Kronos |  |  | 鄒咏霖、李辰暘、汪宸宇、侯思岑 | 2021-03-26 | Closed
14 | Decide the primary features of our term-project platform. |  |  | 鄒咏霖 | 2021-03-29 | Closed
15 | Calculate WBS effort estimation. |  |  | All | 2021-03-29 | Closed
16 | Build a sample software using Jenkins and GitLab. |  |  | 陳熙、李辰暘 | 2021-03-30 | Closed
17 | Prepare textbook Chapter2 slide |  |  | All | 2021-04-12 | Closed
18 | List the requirements of each subsystem |  |  | All | 2021-04-12 | Closed
19 | survey pakage that might be use |  |  | 鄒咏霖、李紹銘 | 2021-04-12 | Closed
20 | develop strategy testing algorithm |  |  | 汪宸宇 | 2021-04-12 | Ongoing
21 | Build Use Case Diagram (SRS) |  |  | 陳熙 | 2021-04-12 | Closed | 陳熙 一併繪製 UseCaseDiagram, SystemArchitectureDiagram
22 | Read Goal-Driven Use Case approach in Chapter 3.5 |  |  | 陳熙 | 2021-04-12 | Closed
23 | Generate System Requirements Specification (SRS) |  |  | All | 2021-04-19 | Closed
24 | Build Functional Requirement (SRS) |  |  | 鄒咏霖、汪宸宇、李辰暘 | 2021-04-19 | Closed
25 | Build System Usage Flow |  |  | 汪宸宇 | 2021-04-12 | Closed
26 | Bulid Interface Requirement (SRS) |  |  | 侯思岑 | 2021-04-12 | Closed
27 | Draw System Architecture (SRS) |  |  | 陳熙 | 2021-04-19 | Closed
28 | Contact Synology Inc. |  |  | 李紹銘 | 2021-04-16 | Closed
29 | Complete WBS Estimation |  |  | All | 2021-04-19 | Closed
30 | Compelte Use Case Specification (SRS) |  |  | All | 2021-04-19 | Closed
31 | Complete SRS and upload to GitLab |  |  | All | 2021-04-20 | Closed
32 | Complete the draft of term project class diagram |  |  | All | 2021-05-01 | Closed