## 工作表1
Software Engineering Meeting Minutes
Date |  | 2021-06-01
Time |  | 11:00~12:00
Location |  | Online
Facilitator |  | 鄒咏霖
Recorded by |  | 鄒咏霖
Objective |  | Project Implementation
Participants
Name |  | E-mail | Role |  |  | Present
鄒咏霖 |  | r09922176@ntu.edu.tw | Host |  |  | v
侯思岑 |  | r08922102@csie.ntu.edu.tw | Member |  |  | v
李辰暘 |  | b06902004@ntu.edu.tw | Member |  |  | v
陳熙 |  | r07922151@csie.ntu.edu.tw | Member |  |  | v
李紹銘 |  | r08922142@ntu.edu.tw | Member |  |  | v
汪宸宇 |  | r09944014@csie.ntu.edu.tw | Member |  |  | v
Meeting Agendas
- final presentation分配
Issues
- presentation (55 mins) - 統整到slide裡面 - (5min)PEP[name=鄒] (4:07) - WBS + 實際完成進度 - Front: react, Backend: flask - (15min) Requirement (做一個presentation版本的，present的時候focus在有做到的) - (3min)System Architecture [name=鄒](3:52) - 簡單講系統需求和對應的 module - (1min) Use Case Diagram [name=汪](7:45) - (10min) Use Case Spec (五個) - (1min) Class diagram [name=岑](1:54) - (26min)Class Breakdown (用 class digram 解釋) - (1min)分工表 - (12 min)Frontend - component對應class - homepage (menu,header) [name=紹銘](2:02) - sideArea(parameter setter)[name=鄒](3:23) - content [name=陳熙](4:14) - Console [name=汪](0:49) - (12min)backend - AlgorithmTester [name=岑](2:56) - Algorithm、BH Algo [name=岑] - ParameterParser [name=暘](3:22) - AssetData[name=鄒](2:25) - DataFileManager [name=汪](4:25) - Calculator[name=汪] - 功能 - 相關的 class : TA, TR, TS - (1min) Sequence Diagram [name=岑](3:34) - single test - (1min)Api[name=鄒](2:06) - (前後端 API) - Jenkins Setup(?)(2:40) - PipeLine: pull -> build -> Unit Test - Demo 影片 (4:01)
Slides
Group |  | Slide URL
Risk Items
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note
1 | Prepare homework paper presentation. |  |  | 陳熙、李紹銘 | 2021-03-08 | Closed
2 | Come up with a real-life process. |  |  | 汪宸宇 | 2021-03-08 | Closed
3 | Survey web frameworks for term project. |  |  | All | 2021-03-08 | Closed
4 | Prepare Amazon presentation. |  |  | 鄒咏霖、陳熙 | 2021-03-14 | Closed
5 | Collect Chaos Report 2016~2020 data. |  |  | 李辰暘 | 2021-03-14 | Closed
6 | Prepare DevOps presentation. |  |  | 鄒咏霖、李紹銘、侯思岑 | 2021-03-22 | Closed
7 | Propose initial requirements for WBS. |  |  | 汪宸宇 | 2021-03-22 | Closed
8 | Contact visiting company candidates. |  |  | 汪宸宇、李紹銘 | 2021-03-22 | Closed
9 | Prepare textbook presentation. |  |  | 李紹銘、侯思岑 | 2021-03-22 | Closed
10 | Try Jenkins and decide whether to use it as our DevOps tool. |  |  | All | 2021-03-22 | Closed
11 | Build Jenkins server on CSIE workstation. |  |  | 陳熙 | 2021-03-22 | Closed
12 | Prepare interview questions for company visits (3 questions each member). |  |  | All | 2021-03-22 | Closed
13 | Watch interviewing videos about Kronos |  |  | 鄒咏霖、李辰暘、汪宸宇、侯思岑 | 2021-03-26 | Closed
14 | Decide the primary features of our term-project platform. |  |  | 鄒咏霖 | 2021-03-29 | Closed
15 | Calculate WBS effort estimation. |  |  | All | 2021-03-29 | Closed
16 | Build a sample software using Jenkins and GitLab. |  |  | 陳熙、李辰暘 | 2021-03-30 | Closed
17 | Prepare textbook Chapter2 slide |  |  | All | 2021-04-12 | Closed
18 | List the requirements of each subsystem |  |  | All | 2021-04-12 | Closed
19 | survey pakage that might be use |  |  | 鄒咏霖、李紹銘 | 2021-04-12 | Closed
20 | develop strategy testing algorithm |  |  | 汪宸宇 | 2021-04-12
21 | Build Use Case Diagram (SRS) |  |  | 陳熙 | 2021-04-12 | Closed | 陳熙 一併繪製 UseCaseDiagram, SystemArchitectureDiagram
22 | Read Goal-Driven Use Case approach in Chapter 3.5 |  |  | 陳熙 | 2021-04-12 | Closed
23 | Generate System Requirements Specification (SRS) |  |  | All | 2021-04-19 | Closed
24 | Build Functional Requirement (SRS) |  |  | 鄒咏霖、汪宸宇、李辰暘 | 2021-04-19 | Closed
25 | Build System Usage Flow |  |  | 汪宸宇 | 2021-04-12 | Closed
26 | Bulid Interface Requirement (SRS) |  |  | 侯思岑 | 2021-04-12 | Closed
27 | Draw System Architecture (SRS) |  |  | 陳熙 | 2021-04-19 | Closed
28 | Contact Synology Inc. |  |  | 李紹銘 | 2021-04-16 | Closed
29 | Complete WBS Estimation |  |  | All | 2021-04-19 | Closed
30 | Compelte Use Case Specification (SRS) |  |  | All | 2021-04-19 | Closed
31 | Complete SRS and upload to GitLab |  |  | All | 2021-04-20 | Closed
32 | Complete the draft of term project class diagram |  |  | All | 2021-05-01 | Closed
33 | Modify the answer of quiz from 咏霖's |  |  | All | 2021-05-04 | Closed
34 | Process Design of SDD |  |  | 鄒咏霖、侯思岑、陳熙 | 2021-05-15 | Closed
35 | UI Design of SDD |  |  | 李辰暘 | 2021-05-15 | Closed
36 | Class Disgram Description |  |  | 李紹銘 | 2021-05-15 | Closed
37 | Sequence Disgram of SDD |  |  | 鄒咏霖、侯思岑、陳熙 | 2021-05-15 | Closed
38 | Data Design of SDD |  |  | 李紹銘 | 2021-05-15 | Closed
39 | Frontend Environment Setting |  |  | 李紹銘 | 2021-05-17 | Closed
40 | (Frontend)React Component Implementation |  |  | 鄒咏霖、汪宸宇、陳熙、李紹銘 | 2021-05-31 | Closed
41 | Backend implementation |  |  | All | 2021-05-31 | Closed
42 | Build our project on workstation of NTUCSIE |  |  | 陳熙 | 2021-06-03 | Ongoing
43 | edit SDD and SRS |  |  | 鄒咏霖、侯思岑 | 2021-06-03 | Ongoing
43 | complete test plan |  |  | All | 2021-06-03 | Ongoing
44 | Prepare present slide |  |  | All | 2021-06-07 | Ongoing